## April HP 2024 Price Confirmatio
Office | Categories | Group Number | Vendor Name | QA Team | Vendor # | Go Notice send from US | Price confirmation Deadline | Price Roll Up Email | Price Confirmation Actual | Price Confirm Leadtime | Price Confirmation Status | PIS send to vendor | Vendor Confirm PIS | PIS Status | Original ETD | Arcadia ETD | Arcadia shipment complete | EC ETD | EC Shipment Complete | WC ETD | WC Shipment Complete | Go Notice Send To vendor | Go Notice Send to vendor Status | GSCP - PIC | GSCP Comment | PD | Holiday Start | Back To Work
CVRO | Bedroom | 100 | HONG MEI | QA Team 1 | 617616 | [14 empty] | 2024-08-10 | TRUE | 2024-07-01 | Complete
CVRO | Upholstery | 92121 | LEATHER MASTER | QA Team 7 | 636147 | [9 empty] | 2023-10-20 | 2024-06-15 | TRUE | 2024-06-15 | TRUE | 2024-06-22 | TRUE | 2023-11-01 | Complete
WBOC | Accessories | A1001080 | KELISS |  | 613923 | 2024-04-19 | 2024-04-24 | [12 empty] | 2024-08-03 | TRUE
WBOC | Accessories | A1001081 | KELISS |  | 613923 | 2024-04-19 | 2024-04-24 | [12 empty] | 2024-08-31
WBOC | Accessories | A1001082 | KELISS |  | 613923 | 2024-04-19 | 2024-04-24 | [12 empty] | 2024-08-03 | TRUE
WBOC | Accessories | A4000669 | AIUE |  | 646821 | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-08-10 |  | 2024-08-03 | TRUE | 2024-08-17
CINRO | Accessories | A4000672 | JAMES ANDREW NEWTON ART |  |  | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-07-06 | TRUE
CINRO | Accessories | A4000673 | MOBEL BAZAAR |  |  | 2024-04-19 | 2024-04-24 | [10 empty] | 2024-08-03 | TRUE | 2024-07-27 | TRUE
WBOC | Accessories | A8000426 | SHIJIE |  | 637187 | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-08-03 | TRUE | 2024-08-03 | TRUE | 2024-08-17
WBOC | Accessories | A8000428 | SHIJIE |  | 637187 | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-08-03 | TRUE | 2024-08-03 | TRUE | 2024-08-17
WBOC | Accessories | A8000431 | SHIJIE |  | 637187 | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-08-03 | TRUE | 2024-08-03 | TRUE | 2024-08-17
CVRO | Accessories | A8010383 | THUONG MY | QA Team 3 | 622820 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-06-22 | 2024-08-24 |  | 2024-08-24 |  | 2024-09-07 |  | 2024-05-03 | Complete
CVRO | Accessories | A8010384 | THUONG MY | QA Team 3 | 622820 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-06-22 | 2024-08-24 |  | 2024-08-24 |  | 2024-09-07 |  | 2024-05-03 | Complete
CVRO | Bedroom | B496 | GRAND WOOD 2 | QA Team 4 | 638807 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-13 | 2024-08-31 |  | 2024-08-31 |  | 2024-09-14 |  | 2024-05-03 | Complete
CVRO | Bedroom | B622 | SAMWELL | QA Team 4 | 641045 | 2024-04-19 | 2024-04-24 |  |  |  | In Process |  |  |  | 2024-07-20 | 2024-07-27 | TRUE | 2024-07-27 | TRUE | 2024-08-10 | TRUE | 2024-05-09 | Complete
CVRO | Bedroom | B833 | GRAND WOOD 2 | QA Team 4 | 638807 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-13 | 2024-09-07 |  | 2024-09-07 |  | 2024-09-28 |  | 2024-04-24 | Complete
CVRO | Bedroom | B895 | VIEW FULL | QA Team 4 | 653746 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-20 | 2024-08-17 |  | 2024-08-17 |  | 2024-08-31 |  | 2024-04-25 | Complete
CVRO | Bedroom | B944 | SHING MARK | QA Team 3 | 900420 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-20 | 2024-08-17 |  | 2024-08-31 |  | 2024-09-14 |  | 2024-04-27 | Complete
CVRO | Dining | D423 | MING YOU | QA Team 1 | 617261 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-05-25 | 2024-07-20 | TRUE | 2024-07-20 | TRUE | 2024-08-03 |  | 2024-04-23 | Complete
ACLO | Dining | D446 | HOMEGUARD CAMBODIA |  | 653747 | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-09-07 |  | 2024-09-14 |  | 2024-09-28
CVRO | Dining | D476 | TRAN VUONG | QA Team 1 | 626675 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-20 | 2024-07-27 |  | 2024-07-27 |  | 2024-08-10 |  | 2024-04-20 | Complete
CVRO | Dining | D494 | WANG FENG | QA Team 4 | 900529 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-13 | 2024-08-24 |  | 2024-08-24 |  | 2024-09-07 |  | 2024-04-24 | Complete
CVRO | Dining | D496 | WANG FENG | QA Team 4 | 900529 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-20 | 2024-08-24 |  | 2024-08-24 |  | 2024-09-14 |  | 2024-04-24 | Complete
CVRO | Dining | D501 | GRAND WOOD | QA Team 4 | 638807 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-06 | 2024-09-21 |  | 2024-09-21 |  | 2024-10-05 |  | 2024-04-25 | Complete
CINRO | Dining | D501 | NEELKANTH |  |  | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-08-17 |  | 2024-08-17 |  | 2024-08-10
CVRO | Dining | D546 | MING YOU | QA Team 1 | 617261 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-06-08 | 2024-07-20 | TRUE | 2024-07-20 | TRUE | 2024-07-20 | TRUE | 2024-04-23 | Complete
CVRO | Dining | D601 | GRAND WOOD | QA Team 4 | 638837 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-06 | 2024-08-24 |  | 2024-08-24 |  | 2024-09-07 |  | 2024-04-25 | Complete
CINRO | Dining | D601 | ISLE |  |  | 2024-04-19 | 2024-04-24 | [10 empty] | 2024-08-17 |  | 2024-08-24
CVRO | Dining | D622 | SHING MARK | QA Team 3 | 900420 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-20 | 2024-08-10 |  | 2024-08-10 |  | 2024-08-24 |  | 2024-04-25 | Complete
CVRO | Dining | D634 | TAM ICH MOT | QA Team 4 | 633105 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-06-29 | 2024-08-10 |  | 2024-07-27 | TRUE | 2024-08-10 |  | 2024-04-23 | Complete
CVRO | Dining | D642 | WANG FENG | QA Team 4 | 900529 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-06 | 2024-07-27 | TRUE | 2024-07-27 | TRUE | 2024-08-10 |  | 2024-04-24 | Complete
CVRO | Dining | D833 | GRAND WOOD | QA Team 4 | 638807 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-13 | 2024-08-31 |  | 2024-08-31 |  | 2024-09-14 |  | 2024-04-24 | Complete
CVRO | Dining | D974 | LAP DAT | QA Team 4 | 613972 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-13 | 2024-08-10 |  | 2024-08-10 |  | 2024-08-24 |  | 2024-04-24 | Complete
CVRO | Outdoor | P207 | EVER YOUNG | QA Team 3 | 652525 | [16 empty] | 2024-07-27 | Complete
CVRO | Outdoor | P213 | EVER YOUNG | QA Team 3 | 652525 | [16 empty] | 2024-06-18 | Complete
CVRO | Outdoor | P284 | HOANG GIANG | QA Team 6 | 636687 | 2024-04-19 | 2024-04-24 | [14 empty] | 2024-05-21 | Complete
CVRO | Outdoor | P572 | HOANG GIANG | QA Team 6 | 636687 | 2024-04-19 | 2024-04-24 |  |  |  | In Process |  |  |  | 2024-08-03 | [6 empty] | 2024-05-09 | Complete
WBOC | Outdoor | P671 | WENTAI |  | 617741 | 2024-04-19 | 2024-04-24
WBOC | Outdoor | P701 | CAC |  | 622432 | 2024-04-19 | 2024-04-24
CVRO | Outdoor | P704 | EVER YOUNG | QA Team 3 | 652525 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-08-31 | 2024-10-05 |  | 2024-11-02 |  | 2024-11-16 |  | 2024-04-26 | Complete
ACLO | Outdoor | P711 | KONDA CAMBODIA |  | 647011 | 2024-04-19 | 2024-04-24
WBOC | Outdoor | P791 | WENTAI |  | 617741 | 2024-04-19 | 2024-04-24 | [9 empty] | TRUE |  | TRUE |  | TRUE
WBOC | Outdoor | P792 | WENTAI |  | 617741 | 2024-04-19 | 2024-04-24 | [9 empty] | TRUE |  | TRUE |  | TRUE
CVRO | Outdoor | P800 | THANG LOI | QA Team 6 | 622390 | [16 empty] | 2024-06-18 | Complete
CVRO | Outdoor | PA572 | HOANG GIANG | QA Team 6 | 636687 | [5 empty] | Complete | [10 empty] | 2024-07-22 | Complete
CVRO | Outdoor | PA704 | EVER YOUNG | QA Team 3 | 652525 | [16 empty] | 2024-07-19 | Complete
ACLO | Occasional | T273 | HOMEGUARD CAMBODIA |  | 653747 | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-09-07 |  | 2024-09-14 |  | 2024-09-21
ATLO | Occasional | T280 | Bear Asia |  | 900352 | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-06-29 | TRUE | 2024-06-29 | TRUE | 2024-07-06 | TRUE
ATLO | Occasional | T285 | Bear Asia |  | 900352 | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-06-29 | TRUE | 2024-06-29 | TRUE | 2024-07-06 | TRUE
CVRO | Occasional | T304 | GLORY 2 | QA Team 4 | 606355 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-20 | 2024-08-17 |  | 2024-08-17 |  | 2024-08-31 |  | 2024-04-23 | Complete
CVRO | Dining | T313 | ANH KHOA | QA Team 7 | 625365 | 2024-04-19 | 2024-04-24 | [7 empty] | 2024-07-13 | 2024-07-13 | TRUE | 2024-07-13 | TRUE | 2024-07-27 |  | 2024-06-03 | Complete
CVRO | Occasional | T315 | ANH KHOA | QA Team 7 | 625365 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-06-15 | 2024-06-15 | TRUE | 2024-06-15 | TRUE | 2024-06-22 | TRUE | 2024-04-24 | Complete
CIRO | Occasional | T322 | PT INAX |  | 653148 | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-09-28 |  | 2024-09-28 |  | 2024-10-12
AMLO | Occasional | T551 | NCS Wood Products Sdn Bhd | QA Team 1 | 634140 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  |  | 2024-08-17 |  | 2024-08-17 |  | 2024-08-31
CINRO | Occasional | T567 | SEVEN HILLS |  |  | 2024-04-19 | 2024-04-24 | [12 empty] | 2024-07-20 | TRUE
CVRO | Occasional | T574 | TRAN VUONG | QA Team 1 | 626675 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-20 | 2024-08-24 |  | 2024-08-24 |  | 2024-08-24 |  | 2024-04-23 | Complete
CIRO | Occasional | T624 | PT SMART |  | 900524 | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-09-07 |  | 2024-09-07 |  | 2024-09-21
CVRO | Occasional | T632 | HONG MEI | QA Team 1 | 617616 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-20 | 2024-08-10 |  | 2024-08-10 |  | 2024-08-24 |  | 2024-04-25 | Complete
CIRO | Occasional | T657 | PT SMART |  | 900524 | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-08-24 |  | 2024-08-24 |  | 2024-09-21
CINRO | Occasional | T667 | AJ CRAFTX |  |  | 2024-04-19 | 2024-04-24 | [10 empty] | 2024-09-07
CVRO | Occasional | T679 | PENG YUAN | QA Team 2 | 628381 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-06-22 | 2024-08-17 |  | 2024-08-17 |  | 2024-08-24 |  | 2024-04-23 | Complete
CINRO | Occasional | T690 | BHANDARI |  |  | 2024-04-19 | 2024-04-24 | [10 empty] | 2024-08-17 |  | 2024-08-17
CVRO | Occasional | T734 | MINH HUY | QA Team 4 | 632409 | 2024-04-19 | 2024-04-24 |  |  |  | Complete |  |  |  | 2024-07-20 | 2024-08-24 |  | 2024-08-10 |  | 2024-08-03 | TRUE | 2024-04-23 | Complete
CIRO | Occasional | T821 | PT INAX |  | 653148 | 2024-04-19 | 2024-04-24 | [8 empty] | 2024-11-02 |  | 2024-11-02 |  | 2024-11-16
WBOC | Wall Unit | W100 | PAITE |  | 606629 | 2024-04-19 | 2024-04-24 | [9 empty] | TRUE |  | TRUE |  | TRUE